Minutes from the teleconference between

WHO HQ and Preparing for Life Initiative (PfL)

4 June 2013

Participants from PfL: Ysbrand Poortman, Martina Ens, Irmgard Nippert, Symone Detmar, Dineke Korfker

Participants from WHO HQ: Valentina Baltag and Charlotte Sigurdson Christiansen

TENTATIVE AGENDA

- Determination of agenda

- Update from both sides

  - see attached PfL- internal communication

  - notes of the teleconf d.d. 14 March 2013

- Action in the regions:

EURO,

EMRO (meetings November?), AFRO (deadline mid August), SEARO,

WPRO (meetings November?), AMRO (meeting September?)

- Proposal for regional and country level action

- Demonstration projects

definition, procedures,

- Acquiring resources

  - UN-institutions, foundations, service clubs, others

  - Strategy (proposal common action, PfL-action, procedures)

- Advocacy document (see attachment)

- Memorandum of Understanding   (see attachment)

- Any other business

Proceedings of the meeting:

- Determination of agenda – agreed

- Update from both sides – discussed and some clarifications was made

  - WHO country office in the Gambia is not informed, Valentina reiterates that in future, when PfL uses the name of WHO, regional and country offices always need to be informed and involved

  - Action points:

    - PfL to send the results of the Gambia study

    - PfL to send preparatory plans for the demo project in the Gambia

- Regional plans:

EURO

Regional meeting planned March 2014

EMRO:

- Anna Rajab is the contact person in Oman, she is waiting for the “green lights” to move ahead with planning the meeting

- A proposal is already developed

- Action points:

  - WHO to share contacts that PfL should copy in on the information

  - WHO to get back to PfL when the regional offices has informed the Oman country office

  - WHO to ask regional office how many countries they envision and how many delegates they wish to have per country

SEARO:

- PfL need some clarification on the first steps in the process outlined in the proposal received from SEARO.

- Action point:

  - PfL to contact SEARO office and copy WHO HQ in the communication

WPRO:

- PfL raised the possibility of using the Manilla meeting as an entry point. WHO HQ reported that they had contacted WPRO and suggested this, but did not yet have a response.

- Action point:

  - WHO HQ to send a reminder message to WPRO colleagues

AMRO:

- There has been initial discussions on making use of the meeting in Washington in September.

- Proposal development: This point was not discussed, other than that WHO suggested that for future proposals, funding for staff in WHO HQ needs to be put in.

- Demonstration projects: PfL raised the question about definition of and criteria for demonstration projects. Due to time limitations, it was agreed to discuss demonstration projects in the next call.

- Acquiring resources - not discussed

- Advocacy document: WHO HQ has developed (soon to be finalized) a policy brief which is to be used as an advocacy document. It is therefore no need to develop another advocacy document, but rather to develop tools that can be used in countries. Action points: WHO to provide PfL with an outline of suggested tools. PfL to consider in countries where they have projects (i.e. Gambia) to use country funds to develop and test tools.think about suggestion for countries

- Memorandum of understanding: PfL is in development of this. Action point: PfL to contact legal departments in WHO to find more about the proceedings

- Any other business: The Regional Advisors meetings for MCA department will be held in Geneva 1-5th July. It was suggested that representatives from PfL could join for the lunch meeting in one of the days in order to meet in person with various regional staff. Action point: WHO to confirm date and time, PfL to check whether they are available to come for a day during that week